Minutes of the working group meeting of Bratislava (Slovakia), 23rd-24th March 2007

Minutes of the Working Group meeting, Bratislava,

Participants: J. Barsics, O. Bonnaud, J. Benlloch, C. Burkley, M. Chmela, D. Deniz, D. Dimitrov, H. Fremont, D. Genon-Catalot, M. Hoffmann, J. Hrad, J. Jasenek, G. Jervan, B. Karaoglan, R. Krivickas, A. Leone-Ganado, J. Ligus, J. Marzo-Lazaro, Z. Mrozek, S. Mylvaganam, G. Papadourakis, D. Pasquet, D. Popescu, D. Rodriguez, H. Roth, J.M. Thiriet, G. Tsirigotis, T. Ward, H. Yahoui,

Excused: J. Burguillo, R. Catthoor, D. Del Corso, J. Filipe, W. Grega, F. Maciel-Barbosa, M.J. Martins, F. Meriaudeau, K. Niel, C. Perra, M. Robert, R. Seaton, A. Seoane, I. Slaidins, S. Stefanova, C. Vaz de Carvalho

-	JMT : Overview of tasks

-	Progress report task by task

o	T3.1 (JMT) Monography

2 documents, 1 for master, one for doctorates

1 contact person by country

Concrete results are expected for Prague

o	T1.1 (TW) Tuning

SSPC created

Some questionnaires already filled by students: need about 1 hour for a non native English speaker

Some already filled by academics: need about 20 min. for a native English speaker

Deadlines: 	dissemination in Prague;

October 2007 end of questions;

End of April available online; (students can fill only one time)

o	T1.3 (DP) Accreditation

Questionnaire is ready, must be filled by a very small number of persons per country, as it is not a statistical study; will be available online soon

o	T2 (TM and DD) e-resources

Expected outputs:  	e-catalogue resource

Quality evaluation

Deliverable: ??? maybe leaving on the eaeeie web site

o	T3.3 (HY) Bologna process in EIE

Questionnaires for students: managed by BEST

Questionnaires for Erasmus coordinators: ready, but recipients must be defined

Exploitation of results ???

-	New project proposal

Brainstorming

I. Friday, 23.03.2007

11.00 - 13.00                EIE Surveyor Managing Team Meeting

- Balance of the advancements of the tasks

- Specification of the topics for the working group meetings

- Discussion

13.00 – 14.00               Lunch (FE STU)

14.00 – 15.15               EIE Surveyor Working Groups Meetings - I

- Introduction

- General Information

- Presentation of the tasks

- The objectives to be achieved during the 2-nd period (until September    2007), workplan

- Division into task groups

15.15 – 16.00               Coffee break

16.00 – 18.00               EIE Surveyor Working Groups Meeting - II

- Working in task groups – first part

19.00 -                         Dinner in Senec (a small town near Bratislava)

II. Saturday, 24.03.2007

09.00 - 10.45                EIE Surveyor Working Groups Meeting – III

- Working in tasks groups – second part

10.45 - 11.00                Coffee break

11.00 - 13.00                - Working in tasks groups – third part

13.00 – 14.00               Lunch (FEI STU)

14.00 – 17.00               - Feedback from the task groups

Thank you all of you for your active participation in the meeting in Bratislava,

Best regards,

Hélène FREMONT & Jean-Marc THIRIET