## Slide 1: Task 1.1
Progress, Bratislava

## Slide 2: Specific & Generic Competences
Questionnaires
Sample size & Collection Methodology
Final Outcome
Dissemination
Timescale
Immediate next steps

## Slide 3: Questionnaires
Minor updates agreed to improve the correlation analysis options between the respondent groups

## Slide 4: Sample Size
Per Project Partner
  200 Student
  20 Employer
  10 Academic
  50 Graduate
Spreadsheet of numbers per Project Partner
Produce instruction set for Project Partners

## Slide 5: Sample Size
We want
  Multi-institution
  Multi-level
  Multi-field

## Slide 6: Collection Methodology
On-line
Paper-based
Two collection periods
  Now until end of current semester (results for Prague)
  September - end October
On-line closes beginning November
Paper-based to Tony Ward asap!

## Slide 7: Final Outcome
Report - full self-contained
The report will look at the alignment of educational programmes to industrial needs hence will be useful for policy makers.
Website containing analysis and results

## Slide 8: Dissemination
Report
  All contributing Institutions (HE & Industrial)
  National Professional Bodies
  National Government Policy Boards
Publications
  Conference / Journal paper(s)
Tuning
  Addition to the Tuning Website

## Slide 9: Timescale
On-line questionnaire live - Early April
Paper-based questionnaires - Early April
Instructions & Targets to all partners - Early April
First set of questionnaires to Tony Ward
  as collected (as early as possible please)
Close of on-line & paper-based - end October
Data entry & collation - end December
Data analysis - end March 2008
Report & Website - end June 2008

## Slide 10: Immediate Next Steps
Amend & test on-line questionnaires
Complete target numbers spreadsheet
Produce partner instructions
Communicate with partners
and
mobilize the team!