## Slide 1: General Meeting Jean-Marc THIRIET Université Joseph Fourier Grenoble
Praha (Czech Rep.),
1. July 2007
děkuji, Jaromir !

## Slide 2: Apologies for absences
K. Niel (AT)
M. Robert (FR)
S. Vanatoru (BEST, RO)
J. Jasenek (SK)
M. Diprose (UK)
R. Seaton (UK)

## Slide 3: Balance THEIERE project 2000-2005 (2004-2005 Dissemination)
Muito obrigado Maria João
final evaluation of the project
=> rated "A"
financial point of view things were not so good

## Slide 4: Agenda (morning)
- 9.00 Welcoming session - 9.30 General information, balance of the administrative and finantial aspects (JM Thiriet) - 10.00 Balance of the TN-Forum (O. Bonnaud) - 10.15 Presentation of the tools for surveys (J. Ligus) - 10.45 Break - 11.00 TASK 1.1 : TUNING (Balance and results of the tasks, organisation of the work for last year, dissemination action of the task) (T. Ward, J. Jasenek) - 11.45 TASK 1.3 : Accreditation (Balance and results of the tasks, organisation of the work for last year, dissemination action of the task) (D. Pasquet, C. Burkley, F. Maciel-Barbosa)

## Slide 5: Agenda (afternoon)
- 14.00 TASK 2 : Quality (Balance and results of the tasks, organisation of the work for last year, dissemination action of the task) (J.L. Marzo-Lazaro, D. Deniz, S. Stefanova) - 14.40 TASK 3 : Bologna-Process Observatory (Balance and results of the tasks, organisation of the work for last year, dissemination action of the task) (JM Thiriet, MJ Martins, H. Yahoui) - 15.20 Dissemination action: J. Barsics - 15.50 Pause - 16.10 General Discussion and Synthesis: (Global balance, global organisation of the work for the last year, global dissemination action) (JM Thiriet) - 17.00 Feedback from the monitoring group (H. Fremont & al.) - 17.20 Feedback from the evaluators (J. Esteves, P. Lappalainen) - 17.40 General conclusion and synthesis

## Slide 6: Running of the project
Wels: December 2006 : Managing Team Meeting
  Discussion with V. de Kosinsky, external evaluator
  Reorganisation of the tasks
    More precise definition of the plannings
    More precise definition of the expected outcomes
Bratislava: 23-24 March 2007: Working group task
  Finalisation and validation of the questionnaires

## Slide 7: Tasks
T1.1 Competences, TUNING (A. Ward, J. Jasenek)
    General competences
    Specific competences
T1.3. Methodology for accreditation
  (D. Pasquet, F. Maciel-Barbosa, C. Burkley)
T2. Internet as educational resource for EIE education
(J.L. Marzo-Lazaro, D. Deniz, S. Stefanova)
T3. Survey, BMD-process in Europe (M.J. Martins, JM Thiriet)
  T3.1. Bologna process in EIE at the bachelor, master and PhD levels
  T3.3 Portal on mobility, EIE curricula (H. Yahoui & J. Ligus) (connection with BEST)

## Slide 8: Tasks
TRANSVERSAL TASK: Portal for the various tasks (J. Ligus)
The monitoring group : Responsible: Hélène Frémont Composition: Juan Carlos Burguillo, Michal Chmela, Sanziana Vanatoru
Two external monitors
  J. Esteves, representing "Entidade Reguladora do Sector Eléctrico" (ERSE), Muito obrigado !
  P. Lappalainen, former President of the EAEEIE, Kiitos !

## Slide 9: General Information

## Slide 10: Coordinator Meeting Bruxelles Brussels, 22-01-2007
2. The role of thematic network projects in the development of the European educational policy (Ettore Deodato, Unit B4, DG EAC)
Thematic networks are one of the most important action of ERASMUS. It is the action of the future.
a. One of the successes is the Tuning action, which is now a prioritary action for harmonisation of disciplines.
b. Another crucial result is the creation of Archipelagos (one in humanities, one in science and technology). In 2009 the European Commission which launch the year of Education and Culture. TN and archipelagos will have to work with the European Commission.
organisation TN Forum May 2007 Brussels : O. Bonnaud, M. Hoffmann, MJMartins, T. Ward, Jan Ligus, J.V. Benlloch, H. Yahoui
+ evaluation of the TN Forum 22nd June 2007: O. Bonnaud
c. A third very important result, the focus will be university and companies. The European Commission (Lisbon Declaration) consider this point important (should work with micro-companies).

## Slide 11: Coordinator Meeting Bruxelles Brussels, 22-01-2007
Results of the selection 2006 and present situation of ERASMUS TN (Alain Pol, ERASMUS coordinator, Unit P2, EACEA)
- 52 received pre-proposals
- 19 pre-proposals were accepted to prepare a full proposition
- 13 TN and 4 TND, 10 TN and 4 TND were accepted.
! In 2007, we should propose a complete proposal, directly (no pre-proposal) !
No dissemination action

## Slide 12: Coordinator Meeting Bruxelles Brussels, 22-01-2007
ANALYSIS OF FINAL REPORTS => FINAL REPORTS
a. Objectives, results and products (products annexed to the report)
b. Coherence between Workplan and activities carried out during life of the project
c. Partnership
d. Project management
e. Financial management
f. Evaluation
External Evaluation => we should achieve this phase with professional organisations which are the actual beneficiaries of the network.

## Slide 13: Communication
New website
- Result part
flyer

## Slide 14: Communication (new web site)
Merci Denis Genon-Catalot

## Slide 15: Communication (flyer)
Merci Béatrice Gabriel (Nancy)

## Slide 16: Agenda

## Slide 17: BEST conference in Lisbon
Invitation and call for abstracts and papers for BEST Conference on Engineering Education 2007 "Education beyond 2010" 11th - 13th October 2007, Technical University of Lisbon, Portugal Deadline for submission of Abstracts: 15th July 2007 http://www.BEST.eu.org/conference This conference is organised by Instituto Superior Técnico (IST) of Technical University of Lisbon (UTL) and the Board of European Students of Technology (BEST).

## Slide 18: Special session IMEKO « Education and Training in the Measurement field »
September 3-5, 2008
Annecy, France
Thematic of the conference:
  Measurement science in human activity
  Fundamentals of measurement science
  Young fields in Measurement science
  Education and Training in Measurement Science
    Evaluation of human competency
    Evaluation of educational methods
    Measurement science in Education
    Virtual training approaches
  Intelligent and virtual instrumentation
  Please contact jean-marc.thiriet@ujf-grenoble.fr

## Slide 19: New TN ??
European Website (yesterday)
  Pre-call 1st November 2006
  Call 1st March 2007
What has been said in Brussels
  Only one call for next academic year (no more information at the moment)

## Slide 20: Next meetings
Managing team meeting | Heraklion (Crete) | Friday 30th November-Saturday 1st December 2007
Working group meeting | Grenoble (France) | March 2008
Joint event assessment with BEST | To be defined | To be defined, 3rd year, joint with the Tallinn events?
3rd general meeting | EAEEIE conf 2008, Tallinn (Estonia), | To be defined, end of May, beginning of June
Last meeting, preparation of the Final Report | ??? | End August or September 2008 (end of eligibility period)

## Slide 21: Finantial aspects

## Slide 22
Financial aspects (practical)
Type of costs | Approved budget (€uro) | Community grant (€uro) | Percentage of funding
1. Staff costs | 607 015 |  | 
2. Direct costs |  |  | 
2.a. Travel and subsistence | 438 000 |  | 
2.b Equipment and materials | 5 500 |  | 
2.c Sub-contracting, consultancy and other external services | 78 945 |  | 
2.d Other | 33 756 |  | 
Total for direct costs | 556 201 |  | 
3. General costs | 87 553 |  | 
TOTAL | 1 250 769 | 400 480 | 32,02

## Slide 23: Travel and subsistence costs
Calculation of subsistence costs: 1 per diem / night + ½ per diem for travel (NOT MORE)
Susbsistence costs eligible for external experts coming from outside Socrates countries (but not Travel costs)
Travel and subsistence costs for students participating to the plenary meeting are eligible

## Slide 24: Co-financing for « Travel and subsistence » and « other costs »
Declaration of costs (travel, accomodation) as co-financing of your institution for « travel and subsistence »
  Other travel and subsistence (for instance days for your participation to the EAEEIE conference)
Declaration of costs (registration) as co-financing of your institution for « other costs »
  Ex: registration for the EAEEIE conference
TAKE CARE ! Only in the eligible zone (EU27 + NO + IS + FL + TR)

## Slide 25: Staff costs – key points
The staff costs related to all persons involved in the project by institution can be charged into the project, according to the time effectively spent => BE REALISTIC !
The costs should be calculated on the hourly, daily, monthly gross cost (salaire brut) multiplied by the number of hours, days or months worked
The beneficiary and partners must keep full and accurate records
Personnel costs should not exceed the norm for the labour market concerned
Volonteer costs (bénévoles) not eligible – real costs only

## Slide 26: Equipment
Hardware and equipments, when > 1000 €uro are submitted to depreciation (33.33 % per annum)
Adjusted to the percentage of use in the project
Pieces of equipment purchased before the project period are not eligible
Be aware of internal rules of depreciation, if different from the Commission’s rules
BILL OF A COMPUTER > 1000 € (around the beginning of the project)
Pour récupérer de l’equipement, il faut que les collègues apportent une facture d’ordino dans la période éligible (début du projet) => on mettra de l’amortissement

## Slide 27: Transfer of money to the partners
POINTS
  Participation to the meetings (+ other events) + automatic co-financing
  Filling of administrative documents
    Co-financing « travel and subsistence »
    Co-financing « other costs »
    Co-financing « equipment »
  Declaration of « staff costs » (not the amount)
  Participation to the tasks (outside of the meetings)
    Manager of tasks
    People who have given specific contributions (development and management of questionnaires, national coordinators for the monograph

## Slide 28: Administrative contact in Nancy
Marie-Lise Lemarquis
ESSTIN
2, rue Jean Lamour
54 519 Vandoeuvre les Nancy cedex
FRANCE
Fax: +33 3 83 68.50.01
Marie-Lise.Lemarquis@esstin.uhp-nancy.fr

## Slide 29: Balance of the Tasks
T1: Competences, TUNING (A. Ward, J. Jasenek)
T1.3. Methodology for accreditation
  (D. Pasquet, F. Maciel-Barbosa, C. Burkley)
T2. Internet as educational resource for EIE education
(S. Stefanova, J.L. Marzo-Lazaro, D. Deniz)
T3. Survey, BMD-process in Europe (M.J. Martins, JM Thiriet)
  T3.1. Bologna process in EIE at the bachelor, master and PhD levels
  T3.3 Portal on mobility, EIE curricula (H. Yahoui & J. Ligus) (connection with BEST)

## Slide 30: Balance of the tasks
Objectives of the task
Present stage of the task
What is required from the EIE-Surveyor partners?
Final outcome of the task for the project

## Slide 31: Synthesis (working group meeting, Bratislava)
1.1 200 students, 20 employers, 10 Academic, 50 Graduate (Surveyor partners responsible) 4
1.3 Surveyor partner 1
2 : forms later
  1 for Surveyor partners (e-CAT): 5 pedagogical resources (link information)
  1 for Quality evaluation (1 for students, 1 for teachers) a class on a specific topic (for each Surveyor partner)
    5 or more resources (per partner)
    Pilot : http://193.140.45.100/pilot2/
    Implementation of questionnaires
3. Monograph (national contacts)
3.3 students
  BEST students (BEST board), 200 students (surveyor contact) 1
  surveyor contacts and people in charge of mobility (surveyor contact) 2

## Slide 32: Balance of the Tasks
T1.1: Competences, TUNING (A. Ward, J. Jasenek)
T1.3. Methodology for accreditation
  (D. Pasquet, F. Maciel-Barbosa, C. Burkley)
T2. Internet as educational resource for EIE education
(S. Stefanova, J.L. Marzo-Lazaro, D. Deniz)
T3. Survey, BMD-process in Europe
  T3.1. Bologna process in EIE at the bachelor, master and PhD levels (M.J. Martins, JM Thiriet)
  T3.3 Portal on mobility, EIE curricula (H. Yahoui & J. Ligus) (connection with BEST)

## Slide 33: What to do? (each partner)
Questionnaire
  deadline 15th November 2007
200 students
  Questionnaire Tuning students (T1.1)
  Questionnaire mobility students (T3.3)
20 employers (1st or 2nd line manager of graduates)
  Questionnaire Tuning employees (T1.1)
10 academic
  Questionnaire Tuning academic (T1.1)
50 Graduate
  Questionnaire Tuning graduate (T1.1)
Questionnaire mobility: people in charge of mobility (T3.3)
  Under the responsibility of the EIE-Surveyor partner
Questionnaire mobility: eie-surveyor partner (T3.3)
E-catalog (at least 5 ressources per institution) (T2)
Quality evaluation of an internal resource (with 20 students) (T2)
Quality evaluation of an external (outside institution) resource (with 20 students) (T2)

## Slide 34
Basic info of QP
http://laraweb.fei.tuke.sk/questionnaires/
http://laraweb.fei.tuke.sk/questionnaires/registration.php?link=1L3J4a1c3n4k1o3a
STEPS FOR MEMBERS OF EIE-Surveyor
http://laraweb.fei.tuke.sk/questionnaires/help

## Slide 35: What to do? (each partner)
Staff-cost declaration 2nd year
(October 2006-September 2007)
  + 1st year (1st and 2nd semester, if not done)
Travel and subsistence meeting of Prague
Co-financing for « travel and subsistence » + « other costs » (2nd year) (+ 1st year, if needed)
Declaration of a computer (> 1000 €, bought at the beginning of the project
Missing documents (written agreements, previous meetings declaration)
PLEASE KEEP RECORD OF THE ADMINISTRATIVE DOCUMENTS YOU SEND TO US (justifications, co-financing)

## Slide 36
National contacts
  Accreditation group (T1.3)
    Please contact D. Pasquet
  Bologna-process in Europe (T3.1)
    List is ready
  Dissemination (contact with Ministries and National associations and bodies)
    Please contact J. Barsics

## Slide 37: National contacts for Bologna-process (T3.1)
AT: K. Niel
BE-V : R. Catthoor
BE-W : J. Barsics
BG : D. Dimitrov
CY : D. Deniz
CZ : M. Chmela
DE : M. Hoffmann & H. Roth
DK: ?
EE: G. Jervan
ES: J. Benlloch and A. Suarez
FI: J. Salo
FR : Club EEA
GR: G. Tsirigotis and G. Papadourakis
HU: C. Csink
IE: C. Burkley
IS: I. Atli Benediktsson
IT: C. Perra
LT: R. Krivicas

## Slide 38: National contacts for Bologna-process (T3.1)
LU : JM Thiriet
LV: I. Slaidins
MT: A. L. Ganado
NL ???
NO: S. Mylvaganam
PL: W. Grega
PT: F. Maciel-Barbosa and MJ Martins
RO: D. Popescu
SE: S. Stefanova
SI: ????
SK: J. Jasenek
TR: D. Deniz, B. Karaoglan
UA: A. Zynovchenko
UK: T. Ward and M. Diprose

## Slide 39: Testing phase: Tool for questionnaire
D. Dimitrov (BG)
N. Bencheva (BG)
Y. Ruseva (BG)
L. Lhotska (CZ)
M.Chmela (CZ)
M. Hoffmann (DE)
E. Sayrol (ES)
D. Pasquet (FR)
H. Yahoui (FR)
JM Thiriet (FR)
G. Tsirigotis (GR)
C. Perra (IT)
R. Krivickas (LT)
S. Mylvaganam (NO)
Z. Mrozek (PL)
Mr Gaciar, lga@pk.edu.pl (PL)
MJ Martins (PT)
I. Casian Botez (RO)
A.E.Ward (UK)

## Slide 40: New project
Content ?
Organisation ?
Salary and skills
Relationships acad. Ind. (SMEs)
Gov. Pol. Likeages, foster or hinder relationships
Contracts with employments with new graduate
  Interest International programmes
Enterprise and entrepreneurship (SMEs)
Link with a sociological group (multiculturalism, gender issue..)
Open outside Europe (D. contact with VN and China), Latin America
Professional registration (after undergraduate studies)
Have a dissemination of existing resources (developed in other projects), catalyzor, and disseminate good results
EIE
Development of criteria for selection of students in EIE
Final master thesis students (requirements, expectation to allow mobility => recognition of the thesis prepared in another country)
Create a network for mobility inside Europe
LLL (use of the resource repository as good way for SMEs to get new information, and for continuous learning…), development of core-curricula specifically for companies
Research part ???
Final products

## Slide 41: TASKS

## Slide 42: Tasks 1.1 Competences, Tuning
Dissemination of questionnaires
Targets of the questionnaire
    Students (200 students, 20 employers, 10 Academic, 50 Graduate) per partners
      Multi-institution, multi-level,
      Strategy, deadline: ?????
    Graduate (200 students, 20 employers, 10 Academic, 50 Graduate) per partners
      Strategy, deadline : ?????
    Employees (200 students, 20 employers, 10 Academic, 50 Graduate) per partners
      Strategy, deadline : ?????
    Academics (200 students, 20 employers, 10 Academic, 50 Graduate) per partners
      Strategy, deadline : ??????
Final outcomes, « report on Tuning in EIE »
  Shape : report, web-site ???
  Strategy, Targets of this final outcome ?????
  Date of availability of the final outcome
Implementation of the questionnaire
  Website of Jan
  Website of the Tuning project (Univ. Deusto) (to be contacted)

## Slide 43: Tasks 1.3 Accreditation
Dissemination of questionnaire
Targets
    National coordinators
      Strategy, deadline : ??????
Final outcomes, « ????????? »
  Shape : report, web-site ??? For accreditation bodies
  (+ an abstract for the monograph)
  Strategy, Targets of this final outcome ?????
  Date of availability of the final outcome
Implementation of the questionnaire
  Website of Jan

## Slide 44: Tasks 2 Quality on on-line pedagogical resources
Dissemination of questionnaire
Targets
    ????
      Strategy, deadline : ?????
    ?????
      Strategy, deadline : ??????
    ?????
      Strategy, deadline : ???????
    ?????
      Strategy, deadline : ??????
Final outcomes, « ??????? »
  Shape : report, web-site ???
  Strategy, Targets of this final outcome ????
  Date of availability of the final outcome
Implementation of the questionnaire
  ???????

## Slide 45
2 sites
  2008 : recupérer le maximum de ressources
  Students:

## Slide 46: TASK 3

## Slide 47: Tasks 3 (Monograph, Bologna Process)
Dissemination of questionnaires
Targets
    Contact person in each country
      Strategy, deadline : direct exchange of documents
Final outcomes, « Monograph on EIE in Europe» and
« Monograph on PhD studies in EIE in Europe »
  Shape : report and web-site (downloadable PDF version)
  Strategy, Targets of this final outcome: Ministries for Higher Education, universities in Europe, universities outside Europe, ?????
  Date of availability of the final outcome: June 2008
Implementation of the questionnaire
  Direct exchange of data (no use of website questionnaire)

## Slide 48: Content of the monograph
Glossary (B. Karaoglan)
International programmes (H. Roth & G. Jervan)
Review on BMD in Europe (H. Yahoui)
Snapshot of national situation (P. Benlloch)
Accreditation (task 1.3)
Synthesis on PhD studies (M. Hoffmann, O. Bonnaud)

## Slide 49: Organisation
Website for the monograph
  Organised (per country, per level)
Printed version of the monograph
  Just for the EC, and some « politicians »
Inform the Commission in order to put the link to our results from the website of Bologna process

## Slide 50: Partners
AT: K. Niel
BE-V : R. Catthoor
BE-W : J. Barsics
BG : D. Dimitrov
CY : D. Deniz
CZ : M. Chmela
DE : M. Hoffmann & H. Roth
DK: ?
EE: G. Jervan
ES: J. Benlloch and A. Suarez
FI: J. Salo
FR : Club EEA
GR: G. Tsirigotis and G. Papadourakis
HU: C. Csink
IE: C. Burkley
IS: I. Atli Benediktsson
IT: C. Perra
LT: R. Krivicas

## Slide 51: Partners
LU : JM Thiriet
LV: I. Slaidins
MT: A. L. Ganado
NL ???
NO: S. Mylvaganam
PL: W. Grega
PT: F. Maciel-Barbosa and MJ Martins
RO: D. Popescu
SE: S. Stefanova
SI: ????
SK: J. Jasenek
TR: D. Deniz, B. Karaoglan
UA: A. Zynovchenko
UK: T. Ward and M. Diprose

## Slide 52: Task 3.3 (portal on mobility)
Dissemination of questionnaires
Targets
    BEST, ERASMUS students
      Strategy, deadline : end of October
    Relationship coordinators and surveyor contact
      Strategy, deadline : end of October
    Final outcomes, « ?????? »
  Shape : report, web-site ???
  Strategy, Targets of this final outcome ????
  Date of availability of the final outcome
Implementation of the questionnaire
  Website of Jan

## Slide 53
Tuning students + 3.3 students (target student), Pepe, Albert, Saba,
Tuning employers : Bahar, Joseph B., José-Marzo Daniel R.,
Tuning Academic: Michael, Dorin, Hamed, Michal
Tuning Graduate: Denis, Derviz, Dimiter, Jan
Accreditation TASK 1.3 (target: EIE partners): Hubert, Gert, Olivier,
TASK 3.3 (target: Surveyor contacts) and TASK 3.3 (target: People in charge of mobility): Daniel P., Cyril, Romanas, Jean-Marc

## Slide 54
External Evaluation => we should achieve this phase with professional organisations which are the actual beneficiaries of the network.
Have a guide for « organisator of meetings »

## Slide 55: T1.1
Regarding the Tuning task - the latest position is that we have finalized the questionnaires and have carried out a small pilot test of them. Jan is currently computerizing them so the next major task, apart from checking everything is spot on, is to plan and task delegates within each Country to muster some returns. This needs to be the task in Bratislava as far as I see it.

## Slide 56: ARCHIVES

## Slide 57
Per diem
Country | Maximum in € | Country | Maximum in €
BE Belgium | 150 | IS Iceland | 183
DK Denmark | 179 | LI Liechtenstein | 174
DE Germany | 127 | NO Norway | 171
GR Greece | 113 | BG Bulgaria | 157
ES Spain | 141 | CZ Czech Rep. | 214
FR France | 130 | EE Estonia | 129
IE Ireland | 165 | CY Cyprus | 100
IT Italy | 130 | LV Latvia | 174
LU Luxembourg | 143 | LT Lithuania | 126
NL Netherlands | 148 | HU Hungary | 136
AT Austria | 122 | Malta | 86
PT Portugal | 143 | PL Poland | 227
FI Finland | 156 | Romania | 185
SE Sweden | 157 | SI Slovenia | 148
UK United Kingdom | 199 | SK Slovakia | 164
 |  | TR Turkey | 138

## Slide 58: Missing written agreements (December 2006)
EAEEIE
Technische Universität Graz
Universiteit Gent
Haute École de la Province de Liège "Rennequin SUALEM«
Technical University, Sofia
University of Cyprus
edaw, s.r.o., CZ
MA&T Sell & Partner GmbH, DE
Fraunhofer-Institut Digitale Medientechnologie
Fachhochschule Würzburg-Schweinfurt
Universitat de Barcelona
Chapitre Education de la section française de IEEE
Université d’Angers
Université de Bourgogne/IUT Le Creusot
Université Claude Bernard Lyon 1
Université de Rennes 1
Institut National des Sciences Appliquées de Rouen
Háskóli Íslands
UNIVERSITÀ DEGLI STUDI DI NAPOLI FEDERICO II
Politechnika Krakowska im. Tadeusza Kościuszki
Delphi, PL
Instituto Superior de Engenharia de Lisboa
INSTITUTO POLITÉCNICO DO PORTO
Kungliga Tekniska högskolan
Uppsala universitet
Boğaziçi Üniversitesi
University of York
Technοlogical Educational Institute of Crete

## Slide 59: Finantial aspects: missing documents (December 2006)
Staff costs (1st and/pr 2nd semesters)
  1, 9, 12, 15, 20, 21, 25, 30, 32, 35, 39, 43, 47, 52, 53, 57, 58, 59, 62, 64, 68, 70, 72, 76, 77, 78, 83, 84, 86, 87, 92, 94, 98, 101, 106, 108
Meeting of Lyon, missing justifications
  Denis and Tony
Meeting of Santander, missing justifications
  partners 9, 62, 72, 77, 85, 103, 109
Meeting of Craiova
  Partners 19, 26, 32, 36, 37, 58, 74, 85, 87, 99, 103, 109, 114
Co-financing: missing justifications
  1, 4, 5, 7, 9, 11, 12, 15, 16, 20, 21, 22, 25, 26, 27, 30, 34, 35, 36, 39, 40, 47, 48, 50, 51, 52, 53, 54, 55, 56, 59, 62, 64, 65, 66, 68, 69, 70, 71, 72, 73, 75, 77, 78, 79, 80, 83, 84, 85, 86, 87, 88, 91, 92, 94, 97, 98, 101, 104, 105, 106, 107, 108, 109

## Slide 60: Deadlines
Validation of the contents of the questionnaire (point of view of targets => use of targets)
  15th April 2007 ?
Implementation of the contents ready
  22th April 2007 ?
On-line validation of the questionnaire (with targets (?) => until beginning of May 2007)
Publication of the questionnaire
  15th May 2007