## Slide 1: Cataloguing and Quality Assessment of Some Resources in EIE Available Through the Internet
Dervis Z. Deniz, Jose L. Marzo
Surveyor T2
Grenoble, 14-15 March, 2008.

## Slide 2: TO DO – General Meeting, Grenoble
Stage of the Task
What remains to be done ?
  Who will do what ?
  Until when ?
Final outcome /results ?
  Content form (CD,Website or report,…)
  What should be done to finalize outcome
Dissemination

## Slide 3: T2 objectives: a schematic description
INTERNET
(EIE resources)
E-CAT
SCORM based
description
E-SURVEY
Quality assessment
questionnaire
Pilot 1,2,3 & 4
E-mailing supporting system
E-mailing DB
Surveyor contact persons

## Slide 4: TO DO – General Meeting, Grenoble
Stage of the Task
  Objective: Development of METHODOLOGY for QA of some learning/educational resources available over the Internet in the field of EIE
  The above has been achieved.
  A realization of the methodology based on web interfaces and the necessary databases completed.
  Testing has been completed.
What remains to be done? (Who will do what? Until when?)
  Porting of Pilot v4 to Dept. Server, Mar 2008. DD
  Actual use of the methodology with real data. All Partners
  Integration of the Contact Management module. DD+JLM
  Use of the statistics module to be realized. DD
  Synthesis from the data to be collected. DD+JLM+ anyone who wants to join.

## Slide 5: T2 Timeline Updated (“Grenoble”) 14-15 Mar., 2008
today

## Slide 6: TO DO – General Meeting, Grenoble
What remains to be done? (Who will do what? Until when?)
  Porting of Pilot v4 to Dept. Server, Mar 2008. DD
  Actual use of the methodology with real data. All Partners
  Integration of the Contact Management module. DD+JLM
  Use of the statistics module to be realized. DD
  Synthesis from the data to be collected. DD+JLM+ anyone who wants to join.

## Slide 7: Strategies for data collection and survey
Data collection for e-cat
  Ask 110 Surveyor partners to provide 5 internal + 5 extra-Institutional, resources for the e-cat (through the EIE contact person)
On-line survey
  Each EIE contact person will be requested to direct a group of students (e.g. a class of 20-25) to evaluate e-resources in the e-Cat (each student to evaluate one local? and one external site related to their courses).

## Slide 8: TO DO – General Meeting, Grenoble
Final outcome /results ?
  Report, Paper(s), on Methodology for QA
    EAEEIE 07 published, Abstract for SEFI 08 accepted and EAEEIE 08 ? Overdue ??
  E-Cat and E-Surv website that can be used beyond the lifetime of the project
    A tool for managing contact persons e-mailing has been developed
    These tools will be useful for EAEEIE, SMEs and the next proposal...
  Plus Point to finalize outcome: a method for using the statistics collected for QA star-rating ?
    Ask users to help with the ways to utilize statistics?
  Allow authorised users to download the e-Surv database for research into QA.

## Slide 9: TO DO – General Meeting, Grenoble
Dissemination
  A flyer section to introduce the Methodology and the web site address.
  Use of the web site to determine interested parties who have not registered to be encouraged to register and either ADD e-cat info or to do survey.
  Use of the tool by interested parties perhaps under the responsibility of EAEEIE Association.
  Opening up the tool to the rest of the world.

## Slide 10
  Attribution of points
    Who did what during the life time of the project ?
      Initial discussion – SCORM (Santander February 2006 )
      Problem formulation (Web based, 2 separate applications, 2 separate datebases
      Final decision to SCORM
      Development of Pilot V1 (March - July 2006)
      End of year 1 Report (November 2006)
      Presentation of initial web design (Pilot V1) Wels 2006
      Development of the Questionnaire V1 (Wels 2006)
      Implementation of Questionnaire V1 Format v1 (Jan-Mar07)
      Presentation of 2nd web design (Pilot V2) Bratislava07

## Slide 11
    Who did what during the life time of the project ?
      Implementation of SCORM v2, Questionnaire V2 Format v2 - Pilot v3 (April – Jul 2007)
      Presentation of Pilot v3 (Prague, Jul 2007)
      Decision to upgrade the web site, user interfaces and databases (Aug-Sept 2007) Also addition of Contact management software.
      Development of Pilot v4 (Sept – Dec 2007) incl. Statistics Module, e-Cat, e-Surv.
      Presentation of Pilot v4 (Heraklion, Dec 2007)
      Finalization of e-Cat form
      Pilot v4 ready for use with different web browsers (Jan 07)
      Pilot v4 testing by volunteering partners (Feb 07)
      Porting of Pilot v4 to Departmental Server (Mar 07)

## Slide 12
  Who did what during the life time of the project ?
    SCORM --- (list to be provided)
    Modified SCORM --- DD + JLM + others (list to be provided)
    Questionnaire --- DD + JLM + Dennnis, et al (list to be provided)
    PILOTS 1-4 and Real Server --- DD
    Contact Management --- JLM
    Attribution of points to all who have joined the meetings for task 2 and contributed
    Attribution of points to those who have done the testing
    Attribution of points to partner coordinators who will put real data into the e-Cat.