## Slide 1: Task 1.1 - Tuning
Thanks to:
Josef, Nina, Ioana
For their help during this meeting

## Slide 2: Task 1.1 Process
Gather questionnaires
  On-line system
  Paper-based
  Email completed forms
Data entry (non on-line)
Consolidation of data-sets
Descriptive data analysis
Factorial and more detailed data analysis
Summary of results and dissemination

## Slide 3: Task 1.1 - Current Status
Questionnaire status
  On-line submission system
  Paper versions
Data analysis thoughts
Summary of current outcomes (needs to be collated)

## Slide 4: Questionnaire Returns
Austria 1
Belgium 2
Bulgaria 197
Cyprus 3
Czech Republic 2
Denmark 0
Estonia 62
Finland 1
France 315
Germany 5
Greece 240
Hungary 218
Iceland 0
Ireland 137
Italy 85
Latvia 50
Liechtenstein 0
Lithuania 1
Luxembourg 0

## Slide 5: Questionnaire Returns
Malta 0
Netherlands 0
Norway 0
Poland 242
Portugal 2
Romania 40
Slovak Republic 308
Slovenia 7
Spain 135
Sweden 0
Italy 191
UK 100
Others 31

## Slide 6: Questionnaire Returns
Summary numbers:
  Student 1783
  Graduate 282
  Academic 131
  Employer 98
Well short of target at present

## Slide 7: Initial Analysis Thoughts
For every competence
For student cf academic cf employer cf graduate
  Pareto average Importance
  Pareto average Level of development
  Pareto average difference (Importance - Level of Devt)
Comparison between genders
By Institution, Country, Aggregate

## Slide 8: Summary of Current Outcomes
Publications
  Josef - 1 off
  University of Russe, student competence conference proceedings
In progress
  EAEEIE 2008 - 1 off (not yet submitted - ooops!)
  SEFI 2008, abstract accepted, paper now due

## Slide 9: Points Attribution for Contributors
Based on:
  Development of Questionnaire - Tony
  Test and Correct the Questionnaire - Tony, Josef, Helene, Jan, +
  Produce on-line questionnaire - Jan
  Contribution to meetings
    Grid of meeting and engagement of partner
  Based on number of questionnaires submitted
    Grid of number of responses of partner

## Slide 10: Final Outcomes
Report on the analysis (pdf)
  Available from website for download
  Available on any CD Rom produced
Publications
  Based on data analysis
  Based on comparison with other Tuning analyses

## Slide 11: What remains to be done
Chase up more returns
  Josef to chase academics
  Tony to chase for student, employer and graduates
Enter paper and electronic returns
Collate and merge data sets
Analyze data
Prepare final report (pdf)
Prepare page for website
Prepare publications

## Slide 12: Remaining Tasks
Chase up more returns - email sent early next week
  Josef to chase academics
  Tony to chase for student, employer and graduates
Final deadline for completed questionnaires - end May
Enter paper and electronic returns - end June
Collate and merge data sets - mid July
Analyze data - end July
Prepare final report (pdf) - end August
Prepare page for website - end August
Prepare publications - ongoing

## Slide 13: Dissemination Objectives
Tuning - matching supply to demand
Pan-European
  In Country comparisons
  Between Country comparisons
  Perception of important competencies
    Strategic importance to education policy makers
  Perception gaps between surveyed groups
    Strategic importance to University curriculum development
  Gender differences
    EU Widening participation agenda

## Slide 14: Dissemination Actions
Final report
  Minister of Education (Europe)
  Country QAA & Education Authorities (through Country partners) - e.g. UK HEFC, UK HEA Learning Centre
  Professional Engineering Associations
  Partners, Tuning Project Team Leader
Journal papers
  IEEE, European & National Education Journals
Conference papers
  EAEEIE, ITHET, SEFI